## Iteration Estimated Effort
ESERET | Task Name: (Dependencies top to bottom) | [8 empty] | Nikoloz | Marley | Zhu | Mariam | Total | WHITE | Task Name: (Dependencies top to bottom) | [8 empty] | Nikoloz | Marley | Zhu | Mariam | Total
ART |  |  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual |  | PEONY |  |  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[6 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task |  | > | [5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
| Preliminary & | Research | [12 empty] | > | Preliminary & | Registration
| Parallel Tasks |  | WordPress, Btheme, php, etc. |  |  |  | 0 |  | 0 | [5 empty] | > | Parallel Tasks |  | WordPress, host, etc. |  |  |  | 0 |  | 0
|  | Review Site | [7 empty] | 0 | 0 |  |  | 0 | > |  | Research | [7 empty] | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 |  |  |  |  | 0 | > |  |  | WordPress, Web market, Ecommerce |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Gather Requirements | [7 empty] | 0 |  |  |  | 0 | > |  | Gathering Requirements | [7 empty] | 0 |  |  |  | 0
|  | Site Re-Design | [7 empty] | 0 |  |  |  | 0 | > |  |  | Functionality | [6 empty] | 0 |  |  |  | 0
|  | Learn GitHub |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 | > |  | Design | [7 empty] | 0 |  |  |  | 0
|  | Contact Client | [6 empty] | 0 |  |  |  |  | 0 | > |  |  | Layout, formatting, color scheme, etc. |  |  |  | 0 |  | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  | 0 | > |  | Contact Client | [7 empty] | 0 |  |  |  | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
| Design & Build | [12 empty] | 0 | > | Design & Build | [12 empty] | 0
| Iteration 1: | Development |  |  |  |  | 22 |  | 0 |  |  |  |  | 0 | > | Iteration 1: | Development |  |  |  |  | 22 |  | 0 |  |  |  |  | 0
|  | 1 | Learn how WordPress works | Developer | All | 5 | 4 | [6 empty] | 0 | > |  | 1 | Register an account on WordPress for the client | Developer | Nikoloz,Zhu | 0.5 | 0.5 | [6 empty] | 0
|  | 2 | Review website and plan updates | Developer | Marley,Mariam | 3 | 1 | [6 empty] | 0 | > |  | 2 | Learn how WordPress works | Developer | All | 5 | 4 | [6 empty] | 0
|  | 3 | Find out how functionality will work/requirments | Developer | Nikoloz,Mariam | 5 | 4 | [6 empty] | 0 | > |  | 3 | Learn how to make a web market on WordPress | Developer | Mariam | 2 | 1 | [6 empty] | 0
|  | 4 | Plan to add more features and layouts for a more attractive style | Developer | Marley,Mariam | 4 | 3 | [6 empty] | 0 | > |  | 4 | Learn how to implement ecommerce in WordPress | Developer | Nikoloz | 3 | 2 | [6 empty] | 0
|  | 5 | Learn/Refresh knowledge on how to use GitHub | Developer | All | 3 | 2 | [6 empty] | 0 | > |  | 5 | Gather requirements both functional and non-functional that will be necessary for the site | Developer | All | 4 | 2 | [6 empty] | 0
|  | 6 | Contact the client | Developer | All | 2 | 1 | [6 empty] | 0 | > |  | 6 | Draw out website - layout, colors, etc. | Developer | Marley,Mariam | 2.5 | 2 | [6 empty] | 0
[14 empty] | 0 | > |  | 7 | Get familiar with GitHub | Developer | All | 3 | 2 | [6 empty] | 0
[14 empty] | 0 | > |  | 8 | Contact client | Developer | All | 2 | 1 | [6 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[7 empty] | 0 |  | 0 |  |  |  |  | 0 | > | [6 empty] | 0 |  | 0 |  |  |  |  | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
| Iteration 2: | Development |  |  |  |  | 14 |  | 0 |  |  |  |  | 0 | > | Iteration 2: | Development |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | 2 | Preparefor website updates | Developer | Marley,Mariam | 2 | 1 | [6 empty] | 0 | > |  | 1 | Learn how WordPress works | Developer | Nikoloz,Zhu | 5 | 4 | [6 empty] | 0
|  | 3 | Contact the client | Developer | Nikoloz,Mariam | 2 | 1 | [6 empty] | 0 | > |  | 2 | Make a web market on WordPress | Developer | Mariam | [8 empty] | 0
|  | 4 | Find out how functionality will work/requirments | Developer | Marley,Mariam | 5 | 4 | [6 empty] | 0 | > |  | 3 | Implement ecommerce in WordPress | Developer | Nikoloz | 3 | 2 | [6 empty] | 0
|  | 5 | Learn/Refresh knowledge on how to use GitHub | Developer | All | 5 | 4 | [6 empty] | 0 | > |  | 4 | Gather requirements both functional and non-functional that will be necessary for the site | Developer | All | 4 | 3 | [6 empty] | 0
[14 empty] | 0 | > |  | 5 | Contact client | Developer | All | 2 | 1 | [6 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[7 empty] | 0 |  | 0 |  |  |  |  | 0 | > | [6 empty] | 0 |  | 0 |  |  |  |  | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
| Iteration 3: | Development |  |  |  |  | 15 |  | 0 |  |  |  |  | 0 | > | Iteration 3: | [5 empty] | 20 |  | 0 |  |  |  |  | 0
|  | 1 | Redisgn Website | Developer | Zhu, Nikoloz | 6 | 6 |  |  | 1 |  | 5 |  | 6 | > |  | 1 | Finish Ecommerce on squarespace | Developer | Mariam, Marley | 3 | 7 |  |  |  | 3 |  | 4 | 7
|  | 2 | GitHub - Documentation | Developer | Nikoloz | 2 | 2 |  |  | 2 |  | 0 |  | 2 | > |  | 2 | Finish Gathering All Requirments | Developer | Mariam, Marley | 2 | 2 |  |  |  | 1 |  | 1 | 2
|  | 3 | Contact Client | Developer | Zhu, Nikoloz | 2 | 2 |  |  | 2 |  | 2 |  | 4 | > |  | 3 | Implement and Design all the pages of the Site | Developer | Mariam, Marley | 6 | 7 |  |  |  | 3.5 |  | 3.5 | 7
|  | 4 | Make Website Video | Developer | Zhu, Nikoloz | 2 | 2 |  |  | 2 |  | 2 |  | 4 |  |  | 4 | Test the website | Developer | Mariam,Marley | 5 | 5 |  |  |  | 2 |  | 3 | 5
|  | 5 | Launch Website | Developer | Zhu | 1 | 1 |  |  | 0 |  | 1 |  | 1 |  |  | 5 | Launch the website | Developer | Mariam,Marley | 2 | 2 |  |  |  | 2 |  | 0 | 2
|  | 6 | Ecommerce | Developer | zhu | 2 | 4 |  |  | 2 |  | 2 |  | 4 | > |  | 6 | Contact client | Developer | Mariam,Marley | 2 | 2 |  |  |  | 1 |  | 1 | 2
[7 empty] | 0 |  | 0 | 9 |  | 12 |  | 21 | > | [6 empty] | 0 |  | 0 |  |  |  |  | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
[7 empty] | 0 |  | 0 |  |  |  |  | 0 | > | [6 empty] | 0 |  | 0 |  |  |  |  | 0
[14 empty] | 0 | > | [13 empty] | 0
[14 empty] | 0 | > | [13 empty] | 0
| Total |  |  |  |  | 51 | 93 | 42 | 0 | 18 | 0 | 24 | 0 | 42 | > | Total |  |  |  |  | 56 | 103.5 | 25 | 0 | 0 | 12.5 | 0 | 12.5 | 25